Caf@IITK

Document 3 — Project Management & Configuration Report

CS455 Software Engineering Course Project — Team XForce

Deliverable 1 — Requirements, Architecture and Project Setup

26 September 2026

Team: Krishna Kumayu (230576) · Kshitij Gupta (230581) · Rudransh Verma (230881) · Shashi Bhidodiya (230956) · Suryansh Verma (231061)

# Initial Sprint Plan

## 1 Release Roadmap

| Sprint | Dates | Goal | Feeds |
| --- | --- | --- | --- |
| S1 | 27 Sep – 5 Oct 2026 | Identity, Catalogue, Inventory and Slots foundations; order placement is atomic and proven correct under concurrent load; CI green on every PR | — |
| S2 | 6 – 15 Oct 2026 | Modify/cancel order, kitchen operations, agent MVP (heuristic + LLM path), Flutter client wired end-to-end to the core flow | D2 (15 Oct) |
| S3 | 16 – 26 Oct 2026 | Testing depth (adversarial, concurrency, security, failure), observability, remaining NFRs, ≥5 discovered defects fixed | feeds D3 |
| S4 | 27 Oct – 6 Nov 2026 | Performance tuning and measurement, deployment to AWS, cost tracking, final hardening | D3 (6 Nov) |

Cadence rationale: the proposal's “2-week sprints” cannot fit the actual 19- and 22-day gaps between D1, D2 and D3, so the team uses four ~10-day sprints instead, giving two review/retrospective cycles per deliverable window rather than one.

## 2 Sprint 1 Goal

“A student can place an order that atomically reserves inventory and a slot, proven correct under concurrent load (NFR-1, NFR-4, NFR-5), on top of working Identity, Catalogue, Inventory and Slot foundations, with CI green on every merged PR.”

This commits the concurrency test harness into the very first sprint, alongside the CI pipeline, authentication, and a working core order-create path — all prerequisites for the D2 requirement (15 Oct) of a demonstrable core transactional workflow plus agent.

## 3 Active Sprint 1 Backlog

| Jira key | Item |  | Type | Assignee | Points |
| --- | --- | --- | --- | --- | --- |
| ⬜ CAF-n | Repo skeleton: FastAPI + SQLAlchemy scaffold, Flutter Web scaffold, Docker Compose, first CAF-1 PR |  | Task | Kshitij Gupta | 2 |
| ⬜ CAF-n | CI pipeline skeleton: lint, type-check, test, coverage gate, Flutter Web build, secret scan (NFR-41) |  | Task | Suryansh Verma | 2 |
| ⬜ CAF-n | Jira–GitHub integration: install GitHub for Jira app, verify Development panel evidence |  | Task | Kshitij Gupta | 2 |
| ⬜ CAF-n | Concurrency test harness: testcontainers PostgreSQL, load-generation script for NFR-1 (NFR-37) |  | Task | Rudransh Verma | 2 |
| ⬜ CAF-n | US-01 Register as a student |  | Story | Krishna Kumayu | 3 |
| ⬜ CAF-n | US-02 Log in to my own dashboard |  | Story | Krishna Kumayu | 4 |
| ⬜ CAF-n | US-04 Roles cannot exceed their permissions (abuse) |  | Story | Shashi Bhidodiya | 3 |
| ⬜ CAF-n | US-06 Onboard a menu item |  | Story | Shashi Bhidodiya | 3 |
| ⬜ CAF-n | US-10 Browse today's menu |  | Story | Suryansh Verma | 2 |
| ⬜ CAF-n | US-11 Set daily inventory |  | Story | Krishna Kumayu | 1 |
| ⬜ CAF-n | US-13 Portions follow the order lifecycle |  | Story | Rudransh Verma | 4 |
| ⬜ CAF-n | US-14 Configure the service window |  | Story | Shashi Bhidodiya | 2 |
| ⬜ CAF-n | US-16 Pick a pickup slot |  | Story | Suryansh Verma | 3 |
| ⬜ CAF-n | US-19 See an exact price quote |  | Story | Kshitij Gupta | 5 |
| ⬜ CAF-n | US-22 Place an order |  | Story | Rudransh Verma | 3 |
| ⬜ CAF-n | US-23 A failed payment releases my reservation |  | Story | Suryansh Verma | 3 |
| ⬜ CAF-n | US-25 Double-submitting is harmless (abuse) |  | Story | Kshitij Gupta | 3 |
| ⬜ CAF-n | US-30 The rush never oversells (quality) |  | Story | Rudransh Verma | 4 |
|  | Total committed |  |  |  | 51 |
| Member |  | Committed points |  |  |  |
| Krishna Kumayu |  | 8 |  |  |  |
| Kshitij Gupta |  | 12 |  |  |  |
| Rudransh Verma |  | 13 |  |  |  |
| Shashi Bhidodiya |  | 8 |  |  |  |
| Suryansh Verma |  | 10 |  |  |  |

Every member owns at least one story with its own PR and commit trail. Rudransh and Kshitij carry more points because they own the two hardest items — the concurrency proof (US-30, built on US-13/US-22) and the pricing engine (US-19) — and this imbalance should be revisited once §3.4's real capacity numbers are in.

Deliberately deferred to Sprint 2: US-27 (modify order) and US-28 (cancel order) build on the same reservation machinery as US-22/US-30 and are safer to attempt once that machinery is proven correct; US-33–US-35 (kitchen operations) and the full Agent epic (US-39–US-43) need the order pipeline to exist first.

## 3.6 Definition of Ready / Done

### Definition of Ready

- Acceptance criteria are written (Given/When/Then) and unambiguous.

- Dependencies on other stories or infrastructure are identified.

- The story has been estimated by the whole team (planning poker).

### Definition of Done (D1-Issues-Tracker PM-26)

- Code is reviewed and approved by at least one other team member (not the author).

- CI is green: lint, type-check, full test suite, the 80% coverage gate, the Flutter Web build, and the secret scan all pass.

- Tests were added or updated for the change, including a regression test for any bug fixed.

- The Jira issue is moved to Done, linked to its merged PR, with the branch/commit/PR key trail intact.

- The story's acceptance criteria are demonstrably met (shown in the PR description or the sprint review).

- If AI assistance was used for the change, a corresponding entry exists in AI-Engineering-Log.md.

## 3.7 Ceremonies

- Daily standup — short async update (what I did / will do / blockers) in the team channel; a live sync when blockers need it.

- Sprint planning — day 1: confirm capacity (§3.4), point the stories, commit the backlog (§3.5).

- Sprint review — last day: demo working software to the whole team against the sprint goal.

- Sprint retrospective — last day: what went well / what didn't / one change for next sprint, recorded in the team's retrospective notes.

- Carry-over rule: any story not Done at sprint end returns to the product backlog, is re-estimated at the next planning session, and the reason is noted in the retrospective — no silent rollover, no backdating (brief §22).

# 4. Defect & Change-Request Process

## 4.1 Defect (bug) workflow

Bugs use the Bug issue type from first discovery, not created retrospectively before a deliverable (brief §22; D1-Issues-Tracker PM-28, PM-31).

| Field | Values |
| --- | --- |
| Severity | Blocker · Critical · Major · Minor |
| Found by | manual · adversarial · concurrency · security · failure-injection |
| Links | “relates to” its regression test issue; “blocks” the story it was found in, if still open |
| Workflow | To Do → In Progress → In Review → Done, same as other issue types |

The brief (§11) requires at least five meaningful defects or weaknesses discovered and fixed by D3, with at least two found through adversarial, concurrency, security or failure-oriented testing — the “found by” field makes that count auditable directly from the Jira board.

## 4.2 Change-request process

The instructor/TA may introduce change requests after D1 (brief §6). Each is logged as its own issue labelled cr, linked to every requirement, story and epic it touches, and carries an impact-analysis before implementation begins:

| Impact area | What to record |
| --- | --- |
| Requirements | Which FR/NFR/US IDs are added, changed or retired; SRS revision-history entry |
| Architecture | Which SADD components, ADRs or diagrams are affected |
| Implementation | Modules and files touched; new/changed Jira stories and sub-tasks |
| Tests | New or modified test cases; regression risk |
| Schedule | Which sprint absorbs the work; what (if anything) is displaced |
| Cost | Any change to infrastructure, storage or LLM-usage cost |

Only after this analysis is recorded does the CR move to In Progress; the backlog and the current sprint are updated to reflect it explicitly, rather than folding the change in silently.

# 5. Outstanding Items Before Submission

| Item | Owner | Source |
| --- | --- | --- |
| Create Jira project CAF; add team + instructor + TAs | Whole team (kickoff) | §1.1 |
| Fill GitHub usernames; verify git email = Jira email per member | Each member | §1.2 |
| Install GitHub for Jira app; push CAF-1 skeleton PR; capture Development-panel evidence | Kshitij Gupta | §1.5 |
| Import CAF-Jira-Backlog-Import.csv; add “implements” links; copy Jira keys into SRS §6.3 | 1 member | §2 |
| Collect real Sprint 1 capacity per member | Krishna Kumayu (Scrum Master) | §3.4 |
| Run Sprint 1 planning poker; replace placeholder Jira keys in §3.5 | Whole team | §3.5 |
| Confirm proposed roles (§3.1) at the team decision meeting | Whole team | HANDOFF.md §4 item 1 |